## 封页
变更管理工具包资产

## 变更影响与障碍评估
更改推出
组织变更影响追踪器 |  |  |  |  | 受影响的角色
编号 | 业务流程/工作流 | 变更影响类型（如果变更涉及多个区域，选择主要类型） | 变更描述 | 变更影响 | <角色> | <角色> | <角色> | <角色> | <角色> | <角色> | <角色> | <角色> | <角色> | <角色> | 受影响编号 | 预期变更程度 | 预期变更障碍 | 影响时间 | 针对主动使组织为变更做准备提出的缓解/行动计划 | 缓解行动所有者 | 缓解计划状态 | 衡量采用率的 KPI/成功度量
1 | 示例：访问帐户/客户信息 |  | - 无需通话度量的纸质文档；Salesforce 将实时直接记录销售和招聘通话与活动 | - 这代表了<role>的流程变化，并需要一些额外培训和行为强化来提高采用率。 | x | x | [8 empty] | 250 | 中 |  |  |  | 待定 | 已计划 | 待定 - 在识别用户采用率度量时更新
2 | 待定 | [14 empty] | 高
3 | 待定
4 | 待定
5 | 待定
6 | 待定
7 | 待定
|  | 高 | 执行工作和做决策的方式出现重大变化
用户将需要大量培训，才可以在未来完成工作；需要大量新技能
所有主要结构变化（例如新职位）构成“高”影响排名
|  | 中 | 流程、策略、角色和职责的一些变化。
用户将需要一些流程和/或系统培训，才可以支持新技能需求。
工作可能会转移到新部门；工作类别或职位可能会改变
|  | 低 | 流程或策略几乎没有任何变化
需要有限工作培训；几乎不需要新技能
没有结构或报告关系变化

## LeadershipStakeholder 参与度
领导力和利益干系人参与策略
重要利益干系人 （组和个人） | 职能/角色 | 部门（即销售、市场营销、运营等） | 决策者 Y/N | 支持级别 | 高级别参与方法 | 目标和预期 | 利益干系人顾虑或问题 | 参与的战略 | 评论
识别此计划直接或间接影响的主要利益干系人组和个人/人员 | 此组或个人的主要职能或角色是什么 | 领导/利益干系人来自哪个部门？ | 利益干系人是决策者吗？ | 此利益干系人组或个人提供的支持或支持程度如何（这可能会随时间变化） | 基于影响和影响力的水平（请查看利益干系人地图） | 识别了解此组或个人的重要内容。 他们对此计划的动机、激励、目标和预期是什么（这可能会随时间变化） | 识别任何利益干系人与计划相关的顾虑或问题，以及如果未充分解决的潜在影响（这可能会随时间变化） | 关于获得支持、认同和承诺，或消除对变更、障碍、顾虑或问题的任何阻碍，对这些方面的潜在策略是什么？ | 与此组或个人的利益干系人管理相关的备注或评论
<示例> |  |  |  |  | 严密管理
领导团队 |  |  |  |  | 保持满意度
John Doe |  |  |  |  | 监视
商业合作伙伴 |  |  |  |  | 保持了解最新情况
扩大项目团队

## CommunicationsTraining 计划
通信/培训计划
内容 （通信/培训的内容） | 通信或培训 | 原因 （通信目的；然后描述） | 对象 （负责创建） | 受众 | 时间 （减时时间表） | 方式 （通信/培训的典型方法） | 跟进 | 培训日期 | 位置 | 引导者 | 评论
即将推出新支持组 | 通信 | 使受众为发布做好准备 | 主管 | 培训主管 | T-60 | 网络研讨会 | Chatter

## 激励回顾
了解现有激励愿景。哪些外在动机有助于鼓励或阻止变更。请考虑薪酬、津贴、促销条件、绩效管理、现场奖励和其他外在激励。对于变更影响的每个角色类型，您可能需要完成此练习。
当前环境有哪些激励措施？
支持变更的奖励： |  | 对变更造成阻碍的奖励： | 中立奖励：
哪些更改增加关于变更的外在激励平衡？

## WIIFM 问题
对于变更影响的每个角色，提出以下问题，了解如何发掘每个用户组的个人和社交动机。
使用此信息构建通信和培训，分享展现人们关心价值观的成功故事，并为利益干系人的参与策略提供信息。
个人影响
他们最关心可以实现哪些结果？
变更如何更好地帮他们实现这些成果？
变更将如何使工作更轻松？
变更如何提高使用 Salesforce 的体验？
变更如何提高工作效能和效率？
社会影响
变更采用率如何对组织的其他人产生积极影响？
变更如何改进与经理的协作方式？
变更如何改善与同行工作人员的协作方式？
变更如何改进与客户的协作方式？
组织影响
变更如何帮助实现关心的组织目标？

## Data (hidden)
Stakeholder Type | Description |  | Location / Business Unit | Level of Influence | Level of Support | Level of Commitment | Description | Level of Importance
Sponsor | Sole Sponsor for the Project; provides ultimate authority |  | HQ | Not at all Influential | Strongly Support | Unknown | Stakeholder Commitment is unknown at this time | Not at all Important
Initiating Sponsor | Sponsor who established and kicks-off the project or initiative |  | Primary Location #2 | Slightly Influential | Somewhat Support | Informal Contact | Only informal contact or conversations about the upcoming change have occurred | Low Importance
Key Sponsor | Sponsor who provides ultimate authority |  | Global / Int'l | Somewhat Influential | Neutral | Awareness | Aware of imminent change and seems to support change effort | Slightly Important
Primary Sponsor | Sponsor(s) who must be centrally engaged |  | Asia / Pacific | Very Influential | Somewhat Opposes | Understanding | Understands the change effort and accepts the nature and intent of the change | Neutral
Secondary Sponsor | Sponsor(s) who need to be kept informed |  | Primary Location #3 | Extremely Influential | Strongly Opposes | Acceptance | Actively works toward change, invests time in the change effort, helps articulate commitment to goals and expected business outcomes | Moderately Important
Partner | Partners may be internal or external that may effect the change initiative; partners need to be fully on board |  | Canada | Decision Authority |  | Commitment | Articulates change as the norm, articulates their personal ownership and buy-in of the change effort | Very Important
Target / End User | Groups or individuals directly impacted or affected by the change initiative; you may need to change what they think and do, or even what they believe and feel |  | Primary Location #4 |  |  | Owns Change | Actively participates in facilitating change. Changes behavior or procedures to support process changes (including post implementation) | Extremely Important / Critical
Interested Party | Groups or individuals indirectly impacted or affected by the change initiative |  | Primary Location #5 |  |  | Resistance | Individually resistant to change and will passively resist the change effort
[6 empty] | Open Resistance | Openly advocates and articulates resistance to the change effort
Change Role | Description | Profile |  | Level of Impact | Level of Involvement | Level of Interest | Description | Level of Contribution
Sponsor | Sponsors legitimize a change initiative through their show of support. They allocate the essential resources to ensure the success of an initiative. | Individual decision makers who have the authority to legitimize the Project activities Have decision-making role for critical elements of the change Need to be involved in the planning and design stage to ensure buy-in |  | No Impact | Team Member | Enthusiastic | Will work hard to make the change effort happen and be successful | No Contribution Required
Advocate | Advocates may not have any legitimate power to initiate the change, but nonetheless have a stake in its outcome. They typically want the change and attempt to obtain commitment and resources for it; they can also help maintain sponsor commitment. | Individuals and/or groups who have a vested interest in the success of the change Most interested in the realization of expected benefits Are well-positioned to leverage their internal influence and relationships for the project’s benefit Need to be provided coaching and updates on an on-going basis so that they can cascade the change |  | Minimal Impact | Meet Regularly | Helpful | Will lend appropriate support | Minimal Contribution Required
Change Agent | Change Agents play key roles in setting up operations for the change. Change agents champion the change through their visible ownership of the change program and through formal and informal communication. | Integral part of the overall change network Act as a key liaison between project leadership and target stakeholders Help to make change happen on a local level by implementing and reinforcing change messages |  | Neutral | Formal Communications | Hesitant | Holds some reservations and typically will not volunteer | Neutral
Target / End User | Targets / End Users are the individuals affected by the change and are the focus of the change effort (i.e., the groups that must change). As such, they play an important role in the short-term (achieving change) and long-term (sustaining change) success of a project. | Individuals or groups who are highly impacted by the change, and are therefore the major focus of the change effort |  | Moderate Impact | Informal Communications | Indifferent | Will not help; will not hurt or hinder the change effort | Moderate Contribution Required
|  |  |  | Significant Impact |  | Uncooperative | Will have to be nudged | Significant Contribution Required
[6 empty] | Opposed | Will openly state and act in opposition
[6 empty] | Hostile | Will try to block the change effort at all costs
[6 empty] | Unknown | Level of interest is currently unknown