## Cover Sheet
Change Management Toolkit Assets

## Change Impact & Barrier Assessm
Change Rollout
Organizational Change Impact Tracker |  |  |  |  | Impacted Role(s)
# | Business Process / Workflow | Change Impact Type (select the primary type if the change touches multiple areas) | Change Description | Change Implications | <Role> | <Role> | <Role> | <Role> | <Role> | <Role> | <Role> | <Role> | <Role> | <Role> | # Impacted | Anticipated Degree of Change | Anticipated Barrier to Change | Timing of Impact | Proposed Mitigation / Action Plan to Proactively Prepare the Organization for Change | Mitigation Action Owner | Mitigation Plan Status | KPIs / Success Metrics to Measure Adoption
1 | EXAMPLE: Accessing Account/Customer Information |  | - Elimination of paper documentation for call metrics; sales and recruiting calls and activities will be logged real-time, directly within Salesforce | - This represents a change to process for <role>s that will require some additional training and behavioral reinforcement to drive adoption. | x | x | [8 empty] | 250 | Medium |  |  |  | TBD | Planned | TBD - Update following identification of user adoption metrics
2 | TBD | [14 empty] | High
3 | TBD
4 | TBD
5 | TBD
6 | TBD
7 | TBD
|  | High | Significant change to the way work is performed and decisions are made
Users will require extensive training to perform their job in the future; Significant number of new skills needed
All major structure changes (e.g. new job position) constitute a “high” impact ranking
|  | Medium | Some changes to processes, policies, roles, and responsibilities.
Users will require some process and/or system training to support new skill needs.
Work may shift to a new department; job categories or titles may change
|  | Low | Few changes to process or policies
Limited job training required; few to no new skills needed
No structural or reporting relationship changes

## LeadershipStakeholder Engagemen
Leadership & Stakeholder Engagement Strategy
Key Stakeholders (Groups and Individuals) | Function/Role | Department (ie. Sales, Marketing, Ops., etc.) | Decision Maker Y/N | Level of Support | High-Level Engagement Approach | Goals and Expectations | Stakeholder Concerns or Issues | Strategies for Engagement | Comments
Identify Key Stakeholder Groups and individuals/people directly or indirectly impacted by this initiative | What is the key function or role of this group or individual | What department does the leader/stakeholder come from? | Is the stakeholder a decision maker? | What is the level of support or buy-in from this stakeholder group or individual (this may change over time) | Based on level of influence and impact (see stakeholder map) | Identify what is important to understand about this group or individual. What is their motivation, incentives, goals and expectations for this initiative (this may change over time) | Identify any stakeholder concerns or issues related to the initiative and the potential implications if they are not adequately addressed (this may change over time) | What are the potential strategies for obtaining support, buy-in and commitment or for eliminating (or at least minimizing) any resistance to change, obstacles, concerns or issues | Notes or Comments related to stakeholder management for this group or individual
<examples> |  |  |  |  | Manage Closely
Leadership Team |  |  |  |  | Keep Satisfied
John Doe |  |  |  |  | Monitor
IS Business Partners |  |  |  |  | Keep Informed
Extended Project Team

## CommunicationsTraining Plan
Communication/Training Plan
What (The Content of the Communication/Training) | Communication or Training | Why (Communication Purpose; then description) | Who (Responsible for creating) | Audience | When (T-Minus Schedule) | How (Typical Methods of Communication/Training) | Follow-up | Training Dates | Location | Facilitator | Comments
New support group coming | Communication | Prepare the audience for the launch | Executive | Training Lead | T-60 | Webinar | Chatter

## Incentive Review
Take a look at the existing incentive landscape. What extrinsic motivators exist that either encourage or discourage the change. Consider pay, perks, promotional criteria, perfomance management, spot rewards and other extrinsic incentive. You may need to run through this exercise for each role type impacted by the change.
What incentives are play in the current environment?
Rewards that support the change: |  | Rewards that create a barrier to the change: | Rewards that are neutral:
Whats changes could be made to increase the extrinstic incentive balance toward the change?

## WIIFM Questions
For each role impacted by the change, ask the following questions to understand how to tap into personal and social motivators for each user group.
Use this information to craft communications and training, tell success stories that demonstrate the values people care about, and inform stakeholder engagement strategies.
Personal Impact
What outcomes do they care about achieving most?
How does the change better help them achieve these outcomes?
How will the change make their job easier?
How will the change make using Salesforce more enjoyable?
How will the change allow them to improve their job effectiveness and efficiency?
Social Impact
How does their adoption of the change positively impact others in the organization?
How does the change improve the way they work with their manager?
How does the change improve the way they work with their peers?
How does the change improve the way they work with their customers?
Organizational Impact
How does the change allow them to help achieve organizational goals they care about?

## Data (hidden)
Stakeholder Type | Description |  | Location / Business Unit | Level of Influence | Level of Support | Level of Commitment | Description | Level of Importance
Sponsor | Sole Sponsor for the Project; provides ultimate authority |  | HQ | Not at all Influential | Strongly Support | Unknown | Stakeholder Commitment is unknown at this time | Not at all Important
Initiating Sponsor | Sponsor who established and kicks-off the project or initiative |  | Primary Location #2 | Slightly Influential | Somewhat Support | Informal Contact | Only informal contact or conversations about the upcoming change have occurred | Low Importance
Key Sponsor | Sponsor who provides ultimate authority |  | Global / Int'l | Somewhat Influential | Neutral | Awareness | Aware of imminent change and seems to support change effort | Slightly Important
Primary Sponsor | Sponsor(s) who must be centrally engaged |  | Asia / Pacific | Very Influential | Somewhat Opposes | Understanding | Understands the change effort and accepts the nature and intent of the change | Neutral
Secondary Sponsor | Sponsor(s) who need to be kept informed |  | Primary Location #3 | Extremely Influential | Strongly Opposes | Acceptance | Actively works toward change, invests time in the change effort, helps articulate commitment to goals and expected business outcomes | Moderately Important
Partner | Partners may be internal or external that may effect the change initiative; partners need to be fully on board |  | Canada | Decision Authority |  | Commitment | Articulates change as the norm, articulates their personal ownership and buy-in of the change effort | Very Important
Target / End User | Groups or individuals directly impacted or affected by the change initiative; you may need to change what they think and do, or even what they believe and feel |  | Primary Location #4 |  |  | Owns Change | Actively participates in facilitating change. Changes behavior or procedures to support process changes (including post implementation) | Extremely Important / Critical
Interested Party | Groups or individuals indirectly impacted or affected by the change initiative |  | Primary Location #5 |  |  | Resistance | Individually resistant to change and will passively resist the change effort
[6 empty] | Open Resistance | Openly advocates and articulates resistance to the change effort
Change Role | Description | Profile |  | Level of Impact | Level of Involvement | Level of Interest | Description | Level of Contribution
Sponsor | Sponsors legitimize a change initiative through their show of support. They allocate the essential resources to ensure the success of an initiative. | Individual decision makers who have the authority to legitimize the Project activities Have decision-making role for critical elements of the change Need to be involved in the planning and design stage to ensure buy-in |  | No Impact | Team Member | Enthusiastic | Will work hard to make the change effort happen and be successful | No Contribution Required
Advocate | Advocates may not have any legitimate power to initiate the change, but nonetheless have a stake in its outcome. They typically want the change and attempt to obtain commitment and resources for it; they can also help maintain sponsor commitment. | Individuals and/or groups who have a vested interest in the success of the change Most interested in the realization of expected benefits Are well-positioned to leverage their internal influence and relationships for the project’s benefit Need to be provided coaching and updates on an on-going basis so that they can cascade the change |  | Minimal Impact | Meet Regularly | Helpful | Will lend appropriate support | Minimal Contribution Required
Change Agent | Change Agents play key roles in setting up operations for the change. Change agents champion the change through their visible ownership of the change program and through formal and informal communication. | Integral part of the overall change network Act as a key liaison between project leadership and target stakeholders Help to make change happen on a local level by implementing and reinforcing change messages |  | Neutral | Formal Communications | Hesitant | Holds some reservations and typically will not volunteer | Neutral
Target / End User | Targets / End Users are the individuals affected by the change and are the focus of the change effort (i.e., the groups that must change). As such, they play an important role in the short-term (achieving change) and long-term (sustaining change) success of a project. | Individuals or groups who are highly impacted by the change, and are therefore the major focus of the change effort |  | Moderate Impact | Informal Communications | Indifferent | Will not help; will not hurt or hinder the change effort | Moderate Contribution Required
|  |  |  | Significant Impact |  | Uncooperative | Will have to be nudged | Significant Contribution Required
[6 empty] | Opposed | Will openly state and act in opposition
[6 empty] | Hostile | Will try to block the change effort at all costs
[6 empty] | Unknown | Level of interest is currently unknown