## Slide 1: Building a LEVERS Change Management Plan

## Slide 2: Your world is perfectly organized to create the behaviors you’re currently experiencing… Transitioning to a new technology platform or interface can be challenging! It often requires people to adopt new behaviors and ways of working from what they’re used to. Use these recommended steps and templates to drive behavior change that sticks, and help facilitate a smooth transition to the new technology for your organization!

## Slide 3
Social
Personal
Structural
DESIRED FUTURE STATE
The world around us…
creates social, personal,
and structural relationships
that support or inhibit our motivation and ability to behave in specific ways.
SOCIAL
PERSONAL
STRUCTURAL
THE SCIENCE OF BEHAVIOR

## Slide 4
Social
Personal
Structural
STRUCTURES
LEADERSHIP
ECOSYSTEM
VALUES
ENABLEMENT
REWARDS
Formal leaders and informal opinion leader actions and modeling
Stakeholder, employee, partner, and community relationships.
Connection to ideals that intrinsically motivate
Knowledge, skills, data, information, and tools
Technologies, policies, procedures, architectures
Incentives, recognition, performance management
DESIRED FUTURE STATE
Leadership
Ecosystem
Values
Enablement
Rewards
Structure
Successful change is 10x more likely when 4 or more of all 6 LEVERS are engaged.
L
E
V
E
R
S
LEVERS FOR DRIVING CHANGE

## Slide 5: Description A Change Management plan is designed to lay the foundation for successful change and promote shared ownership among business, IT, and program stakeholders for driving organizational readiness and sustainable adoption. You will define the plan in the Get Ready phase, and put it into action during the Roll Out and Manage phases. The subsequent slides will walk you through the plan in more detail. Targeted Outcomes Alignment on a clear set of change management outcomes. Understanding of key obstacles encountered and past barriers to change success. Identification of the foundational behaviors necessary to promote successful and sustainable change adoption. Development of an executable change management plan to build change readiness, drive key behaviors, and support attainment of a defined program objectives. Supporting Tools Change Management Plan Sample Project Schedule (see the MFA Rollout Pack) How to Execute Share the Change Management Plan with stakeholders, leaders, and impacted business units. Refine roadmap based on feedback. Socialize roadmap after alignment with key leaders and stakeholders.
Align on Change Management Plan
Get Ready
Plan for Change
Roll Out
Prepare Users
Manage
Reinforce Change

## Slide 6: Plan for Change
Get Ready
Roll Out
Manage

## Slide 7
Get Ready Phase: Change Management Activities
The Get Ready phase lays the foundation for a successful technology rollout. The primary focus during the Get Ready phase is on clearly defining the intended outcomes and benefits of moving to the new system, and developing a common understanding of the change vision.
Leadership involvement in this first phase is critical; visible leadership champions and sponsors can help to drive understanding of the value and importance of the effort, and help to paint a compelling vision of the future.
We recommend taking the actions outlined on this page to set the stage for successful adoption. Click links to jump to descriptions and detailed guidance for each activity.
Get Ready
Manage
GET READY Phase Activities | 
Leadership | Define the Change Vision & Objectives Build a Leadership Engagement Strategy Align on Change Management Plan
Ecosystem | Conduct a Change Impact & Barrier Assessment Build a Stakeholder Engagement Plan Conduct Change Readiness Assessment(s) Establish a Change Network
Enablement | Develop Communication Plan Develop Training Strategy
Structure | Define Adoption/Success Metrics
Roll Out

## Slide 8: Prepare Users
Get Ready
Roll Out
Manage

## Slide 9
Roll Out Phase: Change Management Activities
Change Management activities during the Roll Out phase are designed to drive user awareness, support, and engagement to ensure a successful rollout. Focus on recruiting support and sponsorship from leaders and key change agents.
During this phase, you will implement the Change Management plan, based on activities performed in the Get Ready phase.
We recommend taking the actions outlined on this page during the Roll Out Phase to set the stage for successful adoption. Click links to jump to descriptions and detailed guidance for each activity.
ROLL OUT Phase Activities | 
Leadership | Execute Leadership Engagement Strategy
Ecosystem | Execute Stakeholder Engagement Plan
Values | Communicate the “What’s In It For Me”
Enablement | Execute Communication Plan Execute Training Plan
Rewards | Conduct an Incentive Review
Structures | Set Up Collaboration Space and Feedback Loops
Get Ready
Manage
Roll Out

## Slide 10: Reinforce Change
Get Ready
Roll Out
Manage

## Slide 11
Manage Phase: Change Management Activities
Effectively reinforcing the change helps to promote and cement technology adoption and discourages users from reverting back to old systems.
Throughout the Manage phase, the focus is around measuring the effectiveness of the change strategies that have been implemented, and fine-tuning the change management plan to achieve enduring results.
We recommend taking the actions outlined on this page during the Manage Phase to set the stage for successful adoption. Click links to jump to descriptions and detailed guidance for each activity.
MANAGE Phase Activities | 
Leadership | Continue to Execute Leadership Engagement Strategy
Ecosystem | Continue to Execute Stakeholder Engagement Plan
Enablement | Continue to Execute Communication Plan Continue to Execute Training Strategy
Rewards | Continue conducting an Incentive Review
Structures | Leverage Feedback Loops Monitor Adoption/Success Metrics
Get Ready
Manage
Roll Out

## Slide 12
Change Management Plan
Get Ready
Roll Out
Manage
Leadership
d
Ecosystem
Values
Enablement
Rewards
Structures
Conduct Change Impact & Barrier Assessment
Define the Change Vision & Objectives
Build a Leadership Engagement Strategy
Build a Stakeholder Engagement Plan
Define & Monitor Adoption/Success Metrics
Develop & Execute Communication Plan
Develop & Execute Training Strategy
Execute Change Management Plan
Conduct Change Readiness Assessment(s)
Set up Collaboration Space & Feedback Loops
Conduct Incentive Review
Communicate the “What’s in it for Me” (WIIFM)
Align on Change Management Plan
Establish a Change Network

## Slide 13: Detailed Guidance and Execution Tools The content within this set of slides contains: Programmatic Change Management Strategies & Supporting Tools LEVERS Strategies & Supporting Tools Additional Tools for Execution

## Slide 14: LEVERS Strategies & Supporting Tools

## Slide 15: Description The Change Vision is a clear articulation of what you ultimately aim to accomplish throughout the change initiative. It can be used to inspire, build awareness, and garner support for the change. Targeted Outcomes ↑ alignment during times of change ↑ understanding of the change ↓ change resistance due to clarity ↑ increased value realization How to Execute Paint the Vision: What does the ideal future look like? Draft a change vision statement that clearly articulates the reason for the change. Pilot Vision: Test out and refine it with trusted leaders, change champions and relevant stakeholders. Communicate: Share the change vision statement with managers to cascade. Reinforce & Refine: Share the vision through multiple channels; refine the messaging based on feedback Who to Involve: Involve your executive sponsor and leaders from impacted BUs in crafting change vision Strategy: Define the Change Vision & Objectives
DEFINITION What the lever is | Formal leaders and informal opinion leaders
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | The actions of these people influence the organization's vision, strategy, priorities, opinions, and decisions
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Do formal and informal leaders encourage, model, and support the desired change?
Leadership
Supporting Tools
Change Vision Statement Worksheet/Template How to Create a Powerful Vision for Change (Forbes) How great leaders inspire action - Simon Sinek, Start with WHY

## Slide 16: Strategy: Build a Leadership Engagement Strategy Description Enlist the support of leaders to help champion and amplify the change vision. Transformation efforts have shown to be 5x more likely to be successful when senior leaders model desired behavior changes.* Targeted Outcomes Active leader engagement throughout the change effort ↓ change resistance ↑ rate of adoption of new behaviors How to Execute Identify: Identify the leaders (both executive and mid-level management) whose support and participation is critical for success Enable: Equip leaders with the tools and understanding to be able to clearly and authentically communicate the change vision. A set of suggested talking points and/or slides can go a long way here! Enlist Support: Ask for leaders to visibly show their support. Symbolic leadership can take many forms--from including the change initiative as a topic during existing team meetings, to participating in a leadership video series, or even demoing how they use it in their work!
DEFINITION What the lever is | Formal leaders and informal opinion leaders
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | The actions of these people influence the organization's vision, strategy, priorities, opinions, and decisions
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Do formal and informal leaders encourage, model, and support the desired change?
Leadership
Supporting Tools
Sample Leadership Engagement Strategies Stakeholder Engagement & Communication Plan Template *Don’t Just Tell Employees Organizational Changes are Coming - Explain Why (HBR)

## Slide 17: Strategy: Conduct a Change Impact & Barrier Assessment Description The change impact assessment is focused on identifying key areas of impact, determining the relative degree of those impacts, and developing targeted change management interventions to proactively address and prepare the organization to successfully adopt the new technology or way of working. Targeted Outcomes Development of mitigation strategies that proactively address identified areas of impact ↑ understanding of the change How to Execute Plan: Review current-state processes and ways of working against future-state processes. Document key “deltas” in the Change Impact Assessment template Assess: Gather input from key subject matter experts (via 1:1 interviews or change impact assessment working sessions) to refine the assessment Document: Summarize & socialize key assessment findings Take Action: Collaborate with business SMEs and leadership on the development of Action Plans / Change Management interventions
DEFINITION What the lever is | The organization's “system of people,” which includes customers, employees, partners, vendors and communities.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Relationships within and between these groups influence how people think, act, and get work done across the organization.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Are customers, employees, partners, vendors, and communities organized and connected in a way that fosters successful change?
Ecosystem
Supporting Tools
Change Impact & Barrier Assessment template

## Slide 18: Strategy: Build a Stakeholder Engagement Plan Description An effective stakeholder engagement strategy lays the foundation for success by involving key stakeholders early in the process to build sustained understanding, commitment, and sponsorship for the transition to the new technology or way of working. Targeted Outcomes Build the new technology for the right people Plan for engaging key stakeholders. ↑ adoption from Go Live day Helps with development of timely & relevant communications to impacted individuals and groups. How to Execute Identify key stakeholders and impacted individuals and groups. Conduct a stakeholder analysis by using the Stakeholder Engagement Strategy Template as a guide. Develop an approach for keeping key stakeholders informed and involved during the transition to the new technology. Track and Monitor engagement progress by defining a set of stakeholder engagement metrics.
DEFINITION What the lever is | The organization's “system of people,” which includes customers, employees, partners, vendors and communities.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Relationships within and between these groups influence how people think, act, and get work done across the organization.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Are customers, employees, partners, vendors, and communities organized and connected in a way that fosters successful change?
Ecosystem
Supporting Tools
Stakeholder Engagement Strategy Template

## Slide 19: Strategy: Conduct a Change Readiness Assessment Description A Change Readiness Assessment provides insight into stakeholder and user preparedness and level of commitment to absorb and adopt the changes that come with a switch to the new tool. Targeted Outcomes ↑ understanding of the level of preparation and commitment to adopt MFA Proactively address identified barriers How to Execute Take a Baseline: Use the Change Readiness Assessment questions to gather data from representatives of impacted groups at the beginning of the transition project. This can be done via survey, focus group, or a 1:1 SME interview format. Document and Take Action: Summarize & socialize key assessment findings. Collaborate with business SMEs and leadership on the development of Action Plans / Change Management interventions Continue to Monitor: Use the same format to take additional Change Readiness measures as the project progresses to measure progress, make additional mitigation plans, and ensure each group is on track.
DEFINITION What the lever is | The organization's “system of people,” which includes customers, employees, partners, vendors and communities.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Relationships within and between these groups influence how people think, act, and get work done across the organization.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Are customers, employees, partners, vendors, and communities organized and connected in a way that fosters successful change?
Ecosystem
Supporting Tools
Change Readiness Assessment

## Slide 20: Description A Change Network is a selected group of individuals representing various parts of the business that will be affected by transition to the new technology. Establishing a change network can help to expand the reach of the core change management team, build grassroots support for the initiative, and develop clear pathways for two-way communication. Targeted Outcomes ↑cross-functional awareness ↑ enablement of peers Establish a channel for two-way dialogue about the transition to the new technology How to Execute Find Change Champions: Work with management to identify Change Champions. Invite identified Change Champions to participate in the network and ask to confirm participation. Develop a Plan: Develop a meeting/communication cadence plan for your Change Champions. Get started: Hold a kick off meeting and execute change network plan. Empower the Group: Give the group advanced access to information and tools for spreading the word. Involve them in the planning of the roll-out and encourage them to be involved. Ask them to gather and provide feedback and act on their suggestions. Strategy: Establish a Change Network
DEFINITION What the lever is | The organization's “system of people,” which includes customers, employees, partners, vendors and communities.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Relationships within and between these groups influence how people think, act, and get work done across the organization.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Social Motivation Social Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Are customers, employees, partners, vendors, and communities organized and connected in a way that fosters successful change?
Ecosystem
Supporting Tools
Change Network Overview Sample Change Network Engagement Tactics Change Network Kickoff Communication
*Recommended for organizations with 30+ employees

## Slide 21: Strategy: Identify and Broadcast “What’s in it for Me” (WIIFMs) Description Communicate clear benefits to appeal to, and connect with, people’s personal interests Targeted Outcomes ↑ personal motivation to adopt the new tool. ↑ understanding of how to get the most out of the new tool How to Execute Empathy Mapping: ID impacted roles. Discover what each group cares about and how adoption will help them. Walk through WIIFM questions to get to the WIIFM of your users. Broadcast the WIFFMs: Incorporate the WIIFMs into the leadership, stakeholder, training and especially communication strategies. Tell Stores and Create Experiences: Create experiences and share stories that help people see the WIIFM in action. Success stories, hands on demos, and shadowing an influencer are ways this can be done.
Supporting Tools
WIIFM Questions
DEFINITION What the lever is | A person's values, motivations and sense of purpose.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | The connection to what people care deeply about influences how a person is intrinsically motivated to think or act.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Personal Motivation
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Do people see a connection between the change and their values, motivations, and sense of purpose?
Values

## Slide 22: Strategy: Develop & Execute a Communication Plan Description The communication plan outlines the overarching strategy and tactical approach for delivery of messaging to impacted stakeholders and users, through the right channel, and at the right time. Targeted Outcomes ↑ alignment of all stakeholders and Salesforce users around the new tool Clearly defined approach for communicating about the new tool ↑opportunity for feedback How to Execute Communication Channels: Conduct a communications channel inventory. Chatter: Create a Chatter group. What: Use the Drip Email Campaign templates to tailor communications for your organization. Additional Strategies to Consider Consider asking your sponsor to send the first message introducing the initiative. Consider using surveys to establish a two-way feedback loop.
Supporting Tools
Communication Plan Template Sample Drip Email Campaign (see the MFA Rollout Pack)
DEFINITION What the lever is | The information, tools, training, and resources available to help people do their jobs.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Access to the right enablement resources influences people’s ability to develop the knowledge and skills required to successfully engage, perform, or change.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Personal Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Do people have the information, training, skills, and knowledge required to enact the change?
Enablement

## Slide 23: Strategy: Develop & Execute a Training Strategy Description Training is critical for providing users with the skills that they need to work effectively with the new technology and processes introduced by the transition to the new technology. Targeted Outcomes An enabled workforce that feels confident in using the new tool and platform effectively to do their jobs. How to Execute Assess Training Needs: Understand the training needs of impacted audience. Plan: Develop training design strategy. Build: Build training materials. Deliver: Deliver training to users. Additional Strategies to Consider Consider designing hands-on experiences for users to try the new tool, such as: lunch-and-learns, office hours, and live demos.
Supporting Tools
Training Plan Template
DEFINITION What the lever is | The information, tools, training, and resources available to help people do their jobs.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Access to the right enablement resources influences people’s ability to develop the knowledge and skills required to successfully engage, perform, or change.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Personal Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Do people have the information, training, skills, and knowledge required to enact the change?
Enablement

## Slide 24: Strategy: Conduct an Incentive Review Description Align existing incentives and look for opportunities to add incentives to bolster adoption. Targeted Outcomes Remove misaligned incentives to feature or product adoption Add additional incentives to boost feature or product adoption How to Execute Use the P’s: Embed the use of the feature as a consideration in the performance management process, promotion criteria, and relevant perks. Eliminate Misaligned Incentives: Look at the existing incentive landscape (performance management, promotion, bonus, pay, perks, etc) and realign any incentives that prevent feature adoption. Link Rewards to Behaviors: Link rewards to desired behaviors or ways of using the new tool, not outcomes to avoid unintended behaviors and gaming of the system. Keep it Simple: Use extrinsic rewards in moderation since an over-reliance on them can erode intrinsic motivation. Think small and symbolic.
Supporting Tools
Incentive Review Worksheet
DEFINITION What the lever is | Formal and informal performance management processes, measures, and incentives.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | Formal and informal incentive structures influence how people are encouraged to behave
TYPE OF INFLUENCE Type of influence on actions/behaviors | Structural Motivation
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics for your organization | Are performance management processes, measures, and incentives designed to promote a smooth transition through change?
Rewards

## Slide 25: Strategy: Define Adoption/Success Metrics Description When users are transitioned to the new technology, it is important to make sure they’re committed to using it. Look for an app or set up an adoption dashboard (ex. Lightning Usage App) that makes it easy to monitor adoption metrics. Targeted Outcomes ↑ Adoption Insights that help admins understand users’ needs and focus on issues that really matter How to Execute Use the Lightning Usage App: Click the App Launcher icon ( ), enter Usage in the search box, and then click Lightning Usage. From the left side pane, click Login Metrics to view the associated data. Adoption Metrics for Consideration:   The Login Metrics page shows login data for password-free, single sign-on (SSO), and username & password login methods, with and without MFA enabled. Data is aggregated for the last 7 days and the last 3 months.
Supporting Tools
Lightning Usage App help
DEFINITION What the lever is | The organization’s system of structures, including technology infrastructure, processes, policies, and business rules.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | The collective set of systems and processes both govern and enable work, how data is handled and shared, and how decisions are made to drive objectives.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Structural Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics | Are the organization’s technologies, tools, infrastructure, processes, policies, and business rules designed to promote a smooth transition through change
Structures

## Slide 26: Strategy: Collaboration Space and Feedback Loops Description Setting up Chatter or Slack as a place for people to collaborate, get updates and information about the new tool, and provide feedback to create an improved experience. Targeted Outcomes ↑ active collaboration among users ↓ change resistance ↑ rate of adoption Improve your rollout through feedback How to Execute Set Up Chatter: Create a Chatter group to:   Communicate information and updates   Connect users to champions   Allow users to share best practices and ask questions   Share stories of success Create a Feedback Loop: Use the Chatter group to periodically gather feedback and insight on how to improve your implementation. Use survey, polling, or post a question.
Supporting Tools
Create and Manage Chatter Groups
DEFINITION What the lever is | The organization’s system of structures, including technology infrastructure, processes, policies, and business rules.
INFLUENCE What this LEVER influences, which can advance or inhibit successful change | The collective set of systems and processes both govern and enable work, how data is handled and shared, and how decisions are made to drive objectives.
TYPE OF INFLUENCE Type of influence on actions/behaviors | Structural Ability
QUESTION TO ASK Consider the following to determine whether this LEVER is advancing or inhibiting successful change, and to inform the development of bespoke tactics | Are the organization’s technologies, tools, infrastructure, processes, policies, and business rules designed to promote a smooth transition through change
Structures

## Slide 27: Additional Tools for Execution

## Slide 28: Change Vision Statement Worksheet
Use the below template as a guide for drafting your change statement:
Currently _____description of current state challenge(s) creating a sense of urgency______. In order to ______description of the gap the change will close.______ we are ____ description of the change(s)_____. Doing so will not only _____description of the anticipated business benefit(s)______, but will also ___description of anticipated benefits for specific roles and/or the additional opportunities the change will open the door to_______.

## Slide 29: __________ Change Readiness Assessment
Category | Question(s)
Business Case | I understand the benefits of using __________ I believe that _________ will enable us to protect our customers’ data
Vision | I understand the vision and key objectives for enabling __________
Communication | I believe that communications have been well-timed and effective I can describe the anticipated business benefits of the project
Leadership | I believe that leadership is engaged and supportive of this effort
Organization Preparedness | I believe that we can successfully implement and adopt __________ as an organization I believe that other business initiatives at <organization> will not have an adverse effect on the success of this project
Culture | I believe my colleagues are motivated and committed to seeing this project become a success I believe that changes brought about by the __________ project are causing stress and/or anxiety at <organization>
Change Readiness (Open-ended) | What are the key concerns within your team regarding the use of __________? As it relates to this change, where will we likely encounter resistance? What will it look like? What are the project risks? Are there any other comments you would like to share?
Using a quantitative, color-coded system (shown, right) determine the level of risk associated with answers provided

## Slide 30: The Change Network Benefits the Program & its Participants
Program Benefits
Improve Communication and Collaboration Communication is most effective when delivered face-to-face by people known to the audience. People want an opportunity to be heard and give their opinion; the Change Champion Network fosters that candid two-way dialogue. Establish Credibility in Communications Communications and key messages have more credibility when delivered through familiar channels and by familiar colleagues or opinion or formal leaders. Collect and Disseminate Data and Feedback More Efficiently Through the Network, we can collect feedback and develop targeted communications and change management activities Explain Project Benefits The network provides key leaders and team members with the knowledge and resources to clearly articulate program benefits
Change Champion Benefits
First to Know Change Champions will be among the first to know about new functionality and features included in upcoming releases. First to Try When possible, Change Champions will be selected to learn about and get exposure to the new technology and capabilities introduced by the program Development Opportunities Participation in the network provides Champions the opportunity to develop and demonstrate valuable change leadership skills Ability to Make a Meaningful Impact Change Champions have the opportunity to influence the success of a pivotal initiative for TR

## Slide 31: Change Champions
Change Champions support change management activities, build awareness, and promote adoption of new tools and ways of working within their teams.
Change Champions
ROLE OVERVIEW:
Peer-level advocates and leaders who play a vital role in implementing change through communication and support.
They attend Change Network check-ins, deliver key messages to their teams, and serve as “eyes and ears” from the field.
  KEY RESPONSIBILITIES:
  Participate in Change Network meetings / check-ins
  Monitor readiness on their teams
  Identify & communicate potential barriers to change
  Facilitate a two-way feedback loop between users and the project; cascade messages to teams
  Serve as a visible advocate for the program
Champions per functional area/team
2-4
~4
Hours per month
Attend Change Network meetings
Share information and gather feedback/questions from team; funnel through the network
Participate in readiness activities as needed (e.g., demos, Office Hours, etc.)

## Slide 32: Sample Change Network Engagement Tactics
Cross-Collaboration Group Model: Connect Champions from different functional areas to share best practices and lessons learned throughout the change initiative
Collaborate Site - Set up a Chatter group or Slack channel specifically for Change Champions to share info. and collaborate
Learning Events: Conduct learning events for Champions, then have Champions host learning events for members of their teams
Corporate Newsletters: Share success stories and spotlight Change Champions and their efforts
Team Challenges: Create competitions to drive interest and anticipation
E.g., Fastest to find a specific piece of info., “fewest clicks” competition to see who can navigate to a particular data set or piece of information in Salesforce during UAT or the Pilot; publish the results
Use Recognition: Leverage existing channels to recognize team members going above and beyond
Champion Updates During Team Meetings: Champions provide updates during Team huddles / weekly meetings
Weekly Updates: One person leads discussion; Change Network members report out progress: training, comms or other people people responsible for various components report out on progress.
Post-Rollout War Room: Keep daily pulse on how things are going; report out on key metrics; resolve immediate issues as quickly as possible; involve management team and champions in running these sessions
“YouTube” Videos & “Did you Know” posters: Short “how to” video clips and/or posters highlighting key features and/or changes. Include change champions in the development/shooting of the videos and posters
Note to users of this template: This is not an exhaustive list of change network engagement tactics; incorporate additional/alternative approaches as you see fit

## Slide 33: Change Network Communication
<Program Name> Champions,
Please save the date for the official kickoff of our <Program Name> Champions Network!
The purpose of this group is to help prepare the organization for the key changes that will accompany the ______ rollout by driving awareness, championing new ideas and ways of working, and creating a channel for two-way feedback each step of the way.
During this kickoff meeting, you’ll have the opportunity to:
Be among the first to hear the latest updates on the <Program Name> program.
Learn more about your role as a <Program Name> Champion and how you can help prepare the organization and our customers for change.
Ask questions, provide feedback, and receive information you can share with your team.
Feel free to reach out to <name> with any questions, and we look forward to seeing you in <timeframe>!
<Signature>
Use the below template as a guide for kicking off communications to your champion network

## Slide 34
Change Management Plan
Get Ready Phase
Roll Out Phase
Manage Phase
Leadership
d
Ecosystem
Values
Enablement
Rewards
Structures